## Annual Procurement Plan
Procuring Entity Name | MINISTRY OF WORKS
Procurement Plan for year | 2022
Date Created | 2022-01-01
Comments
Estimated dates
Category | Description | UNSPSC | Ref No | Envisaged Quantity | Unit | Estimated Budget | BUDGET CODE | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date | PROCUREMENT METHOD RATIONALE
works | Reconstruction of dilapidated mechanical base workshop |  | RSA/56/MOW/MES/1 | 1 | Naira | 5000000 | 34001001/23030113/17000002 | Anambra state Government | N | Selective | 1st April,2022 | 28,April | 1st May,2022 | 14th June,2022
works | Rehabilitation Works At Geneva Hotel Section of Old Inec Road, Awka, Anambra State |  | RSA/67/MOW/MES/1 | 1 | Naira | 10000000 | 34001001/23020114/17000048 | Anambra state Government | N | Selective | 2nd April,2022 | 28,April | 2nd May,2022 | 15th June,2022
works | Rehabilitation Works At Ultimate Plaza Section Of Old Ince Road, Awka, Anambra State |  | RSA/68/MOW/MES/1 | 1 | Naira | 10000000 | 34001001/23020114/17000048 | Anambra state Government | N | Selective | 3rd April,2022 | 28,April | 3rd May,2022 | 16th June,2022
works | Procurement of Office Furniture and fittings/ Equipment |  | RSA/ADM/15 | 1 | Naira | 5000000 | 34001001/23020118/17000006 (This is Okay) | Anambra state Government | N | Selective | 1st April,2022 | 28,April | 1st May,2022 | 14th June,2022
works | Procurement of internet subscription for MOW Road Tracking Portal |  | RSA/57/MOW/MES/1 | 1 | Naira | 5000000 | 34001001/23030121/17000009 | Anambra state Government | N | Selective | 1st April,2022 | 28,April | 1st May,2022 | 14th June,2022
works | Capacity Building for Civil/Mech. Engineers on Civil 3D, Orion, and E-Tabs |  | RSA/58/MOW/MES/1 | 1 | Naira | 5000000 | 34001001/23050101/17000042 (This is Okay) | Anambra state Government | N | Selective | 1st April,2022 | 28,April | 1st May,2022 | 14th June,2022
works | Rehabilitation of MoW borehole |  | RSA/251/MOE/T/1 | 1 | Naira | 2000000 | 34001001/23040105/17000038 (This is okay) | Anambra state Government | N | Selective | 1st April,2022 | 28,April | 1st May,2022 | 14th June,2022
works | Construction of Igbo ukwu – Aguluzigbo road with spur to Umona |  | RSA/2/MOW/H/1 | 1 | Naira | 275000000 | 34001001/23020114/17000046 | Anambra state Government | N | Selective | APRIL,2022 | MAY,2022 | MAY,2022 | NOV, 2022
works | Construction of discharge control within Eke-Awka to discharge at Iyiagu channel, Awka south LGA |  | RSA/45/MOW/MES/1 | 1 | Naira | 171043332.05 | 34001001/23020114/17000047 | Anambra state Government | N | Selective | MAY,2022 | JUNE, 2022 | JUNE, 2022 | DEC, 2022
works | Construction of girls Secondary school Igbo Ukwu – Azigbo road with spur, Aguata LGA |  | RSA/410/MOW/PD/1 | 1 | Naira | 737757596 | 34001001/23020114/17000047 | Anambra state Government | N | Selective | JUNE, 2022 | JULY,2022 | JULY,2022 | JAN, 2023
works | Reconstruction of group of roads in Okpoko Ogbaru LGA |  | RSA/11/MOW/MES/1 | 1 | Naira | 3589775070.53 | 34001001/23020114/17000045 | Anambra state Government | N | Selective | APRIL,2022 | MAY,2022 | MAY,2022 | NOV, 2023
works | Construction of interchange at Esther Obiakor by Ikenga junction of Enugu- Onitsha expressway, Anambra state |  | RSA/55/MOW/MES/1 | 1 | Naira | 5552537702.25 | 34001001/23020114/17000046 | Anambra state Government | N | Selective | JULY, 2022 | AUGUST,2022 | AUGUST,2022 | JAN, 2023
works | Construction of Eke-Awgbu – Mbaukwu road and erosion control |  | RSA/54/MOW/MES/1 | 1 | Naira | 599831686.3 | 34001001/23020114/17000047 | Anambra state Government | N | Selective | APRIL,2022 | MAY, 2022 | MAY, 2022 | DEC. 2022
works | Construction of Prof. Chukwuma Soludo Avenue and Igboukwu-Ikenga-Ekwulobia road with spurs to Isuofia |  | RSA/53/MOW/MES/1 | 1 | Naira | 2135000000 | 34001001/23020114/17000047 | Anambra state Government | N | Selective | JULY, 2022 | AUGUST,2022 | AUGUST,2022 | OCT. 2023
works | Reconstruction of road from Ogbunike post office – 7th mile road – Igwe Umenyiora road – Enugu/Onitsha dual carriageway |  | RSA/389/MOW/PD/1 | 1 | Naira | 1843131853.57 | 34001001/23020114/17000045 | Anambra state Government | N | Selective | MAY,2022 | JUNE,2022 | JUNE,2022 | JUNE. 2023
works | Construction of Amashovel - Umunwaledo - Ohia Obodo - Igwe road Uli, with bridge, |  | RSA/186/MOW/MES/1 | 1 | Naira | 956000000 | 34001001/23020114/17000047 | Anambra state Government | N | Selective | MAY,2022 | JUNE,2022 | JUNE,2022 | FEB. 2023
works | Rehabilitation of major access roads to Ngozika Housing Estste Phase 2 |  | RSA/49/MOW/MES/1 | 1 | Naira | 135000000 | 34001001/23020114/17000046 | Anambra state Government | N | Selective | MAY,2022 | JUNE,2022 | JUNE,2022 | NOV. 2022