## 5No Quick Wins
Procuring Entity Name | MINISTRY PUBLIC UTILITIES
Procurement Plan for year | 2022
Date Created | 2022-01-07
Comments
Estimated dates
Category | Description | UNSPSC | Ref No | Envisaged Quantity | Unit | Estimated Budget | BUDGET CODE | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication Date | Tender Opening Date | Award Date | Project Start Date | Project Completion Date | Certification/Conclusion | PROCUREMENT METHOD RATIONALE
Works | Extension of electricity to various towns and communities:- Rehabilitation/Augmentation/Expansion of solar power system/network in the Ministry for improved work output/performance |  | MPU/AN/EE/Vol.1/03/1 | 1 | NO | 6000000 | 61001001/23020103/14000003 | ANSG | N | SELECTIVE | 2022-01-04 | 14/4/2022 | 29/04/2022 | 2022-01-05 | 14/06/2022 | 20/06/2022 | Timely completion of project and cost effectiveness of the procurement process
Supplies | Fire Service Supplies: Provide & install of 6Nolaptops, 3No TVs, 1No executive table, 2No executive chairs, set executive sofa with center table, 20No regular office tables & chairs, 12No window blinds, 8No 1hp spilt unit Air Conditioners, 3No office size Refrigerators |  | MPU/AN/FSH/VOL.1/03/7 | 1 | NO | 6000000 | 61001001/23020110/14000023 | ANSG | N | SELECTIVE | 2022-01-04 | 14/4/2022 | 28/04/2022 | 2022-01-05 | 14/06/2022 | 25/06/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Provision of Potable Water Supply scheme to Communities across the State:- Rehabilitation of 5No non-functional boreholes at State Secretariat complex including replacement of dislocated pipeline rising mains to the reservoirs, |  | MPU/AN/WR/Vol.1/02/20 | 5 | 1000000 | 5000000 | 61001001/23020105/10000022 | ANSG | N | SELECTIVE | 2022-01-04 | 14/4/2022 | 29/04/2022 | 2022-01-05 | 14/06/2022 | 25/06/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Rehabilitation / Repair of the solar and non solar boreholes in the state (water and supply projects across the state):- Rehabilitation/Conversion of 1No borehole at Isuofia to solar powered hybrid RSI Inverter |  | MPU/AN/WR/Vol.1/35/15 | 1 | 3000000 | 6000000 | 61001001/23020105/10000022 | ANSG | N | SELECTIVE | 2022-01-04 | 14/4/2022 | 29/04/2022 | 2022-01-05 | 14/06/2022 | 25/06/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Establishment of Water Sector Governance Agencies and Institutional Framework:- Rehabilitation/Refurbishing of the HC & PS offices inclusive of sandblasting, complete re-painting, ceiling replacement, replacement of faulty plumbing materials etc |  | MPU/AN/WR/Vol.1/38/46 | 1 | 5000000 | 5000000 | 61001001/23020105/10000051 | ANSG | N | SELECTIVE | 2022-01-04 | 14/4/2022 | 29/04/2022 | 2022-01-05 | 14/06/2022 | 25/06/2022 | Timely completion of project and cost effectiveness of the procurement process
Estimated dates
Category | Description | UNSPSC | Ref No | Envisaged Quantity | Unit | Estimated Budget | BUDGET CODE | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date | PROCUREMENT METHOD RATIONALE
Fire Safety and Services
Works | Construction of Fire Service Station at Ekwuluobia and Ogbunike |  | MPU/AN/FSH/VOL.1/01/20 | 2 | 20000000 | 40000000 | 61001001/23020110/14000027 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Fencing and Landscaping of Fire Service Stations at Ihiala |  | MPU/AN/FSH/VOL.1/02/4 | 1 | 25000000 | 25000000 | 61001001/23020103/14000025 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Supplies | Purchase of Fire Extingushers and chemicals (foam compound) |  | MPU/AN/FSH/VOL.1/03/7 | 1500 | 20000 | 30000000 | 61001001/23020110/14000023 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Supplies | Purchase of uniform protective kits and wears for firemen |  | MPU/AN/FSH/VOL.1/03/12 | 500 | 20000 | 10000000 | 61001001/23010123/14000024 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Refurbishing of 14No Fire Fighting Trucks |  | MPU/AN/FSH/VOL.1/05/10 | 14 | 714285.75 | 10000000.5 | 61001001/23010123/14000029 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Fire Service Projects; Renovation of Amawbia Fire Service Station |  | MPU/AN/FSH/VOL.1/07/12 | 1 | 10000000 | 10000000 | 61001001/23020100//13000001 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Purchase of Fire fighting trucks |  | MPU/AN/FSH/Vol.1/07/25 | 2 | 40000000 | 80000000 | 61001001/23020107/14000026 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Power Supply
Estimated dates
Category | Description | UNSPSC | Ref No | Envisaged Quantity | Unit | Estimated Budget | BUDGET CODE | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date | PROCUREMENT METHOD RATIONALE
Works | Anambra State Rural ElectricityProject Phase III & Completion |  | MPU/AN/EE/Vol.1/01/5 | 1 | 350000000 | 350000000 | 61001001/23020103/14000001 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Rehabilitation and maintenance of street light in Awka and Onitsha |  | MPU/AN/EE/Vol.1/02/5 | 2 | 50000000 | 100000000 | 61001001/23020103/14000002 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Extension of electricity to various towns and communities |  | MPU/AN/EE/Vol.1/03/1 | 1 | 300000000 | 300000000 | 61001001/23020103/14000003 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Traffic control using solar powered traffic lights in Awka and Onitsha |  | MPU/AN/EE/Vol.1/04/7 | 2 | 50000000 | 100000000 | 61001001/23020123/14000000 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Street lightening for Urban centres; Nnewi, Awka, Onitsha, Ekwulobia, Ihiala, Umunze |  | MPU/AN/EE/Vol.1/08/10 | 6 | 336297029 | 2017782174 | 61001001/23020123/14000014 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Water Ways/Resources
Estimated dates
Category | Description | UNSPSC | Ref No | Envisaged Quantity | Unit | Estimated Budget | BUDGET CODE | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date | PROCUREMENT METHOD RATIONALE
Services | New greater Onitsha water scheme |  | MPU/AN/WR/Vol.1/15/18 | 1 | 50000000 | 50000000 | 61001001/23020105/10000001 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Rehabilitation of the greater Onitsha water supply |  | MPU/AN/WR/Vol.1/15/20 | 1 | 5000000 | 5000000 | 61001001/23030105/10000002 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | New Awka Urban water (Amansea Ebenebe water exploitation) |  | MPU/AN/WR/Vol.1/07/25 | 1 | 20000000 | 20000000 | 61001001/23020105/10000003 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | A Nnewi Urb. Water supply scheme |  | MPU/AN/WR/Vol.1/14/05 | 1 | 10000000 | 10000000 | 61001001/23020105/10000004 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Rehabilitation of (Nimo, Enugu Ukwu,Abagana) water scheme |  | MPU/AN/WR/Vol.1/11/23 | 1 | 10000000 | 10000000 | 61001001/23030105/10000005 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Agulu - Aguiyi water scheme |  | MPU/AN/WR/Vol.1/06/15 | 1 | 10000000 | 10000000 | 61001001/23020105/10000006 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Services | Obizi Uga regional water scheme |  | MPU/AN/WR/Vol.1/03/35 | 1 | 10000000 | 10000000 | 61001001/23020105/10000007 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Oraifite / Ozubulu water scheme |  | MPU/AN/WR/Vol.1/05/16 | 1 | 5000000 | 5000000 | 61001001/23020105/10000008 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Services | Aguleri water scheme |  | MPU/AN/WR/Vol.1/04/30 | 1 | 10000000 | 10000000 | 61001001/23020105/10000009 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Uli borehole water scheme |  | MPU/AN/WR/Vol.1/12/09 | 1 | 10000000 | 10000000 | 61001001/23020105/10000011 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Awkuzu / Ifite dunu water suply scheme |  | MPU/AN/WR/Vol.1/25/12 | 1 | 10000000 | 10000000 | 61001001/23030104/10000015 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Oba water supply scheme |  | MPU/AN/WR/Vol.1/08/15 | 1 | 10000000 | 10000000 | 61001001/23030104/10000016 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Ihiala regional water supply scheme |  | MPU/AN/WR/Vol.1/12/27 | 1 | 10000000 | 10000000 | 61001001/23030104/10000017 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Alor water supply scheme |  | MPU/AN/WR/Vol.1/08/14 | 1 | 10000000 | 10000000 | 61001001/23020105/10000018 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Nibo water supply scheme |  | MPU/AN/WR/Vol.1/07/25 | 1 | 10000000 | 10000000 | 61001001/23020105/10000019 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Umunze New water scheme |  | MPU/AN/WR/Vol.1/23/19 | 1 | 10000000 | 10000000 | 61001001/23020105/10000020 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Provision of Potable Water Supply scheme to 10No Commiunties across the State |  | MPU/AN/WR/Vol.1/02/20 | 1 | 200000000 | 200000000 | 61001001/23020105/10000022 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Ongoing Awka water supply scheme(water reticulation and distribution) |  | MPU/AN/WR/Vol.1/07/17 | 1 | 10000000 | 10000000 | 61001001/23020105/10000023 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Rural water supply and sanitation (RUWASSA)/Implementation of Water Safety Plan |  | MPU/AN/WR/Vol.1/40/10 | 1 | 30000000 | 30000000 | 61001001/23020105/10000024 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Partnership for the Expanded water Supply, Sanitation and Hygien - PWASH/Sustainable WASH Activities |  | MPU/AN/WR/Vol.1/41/33 | 1 | 70000000 | 70000000 | 61001001/23020105/ 10000025 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Ojoto water scheme |  | MPU/AN/WR/Vol.1/08/34 | 1 | 10000000 | 10000000 | 61001001/23020105/ 10000026 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Rehabilitation / Repair of the solar and non solar boreholes in the state (water and supply projects across the state) |  | MPU/AN/WR/Vol.1/35/15 | 1 | 3000000 | 3000000 | 61001001/23030104/10000038 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Reconstruction of water corporation into the new urban asset holding corporation |  | MPU/AN/WR/Vol.1/38/24 | 1 | 5000000 | 5000000 | 61001001/23020105/10000040 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Services | Mapping of surface and underground/sub-surface water potentials/sources in the state |  | MPU/AN/WR/Vol.1/38/37 | 1 | 5000000 | 5000000 | 61001001/23020105/10000041 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Replication of hybrid water generation system (combination of conventional submersible pump and panel) as solar source for completed major scheme ; Otuocha, Ihiala, Agulu, Aguinyi, Nibo. |  | MPU/AN/WR/Vol.1/02/25 | 1 | 10000000 | 10000000 | 61001001/23030104/10000042 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Services | Development of design for proposed major water schemes in the state; Awka, Ayamelu, 2nd phase Onitsha water scheme, Nnewi, Ihiala, Otuocha. |  | MPU/AN/WR/Vol.1/38/40 | 1 | 5000000 | 5000000 | 61001001/23020105/10000043 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Reconstruction and rehabilitation of all ADB projects |  | MPU/AN/WR/Vol.1/02/45 | 1 | 5000000 | 5000000 | 61001001/23030104/10000044 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Supplies | Geophysics investigation equipment; terrameter 2000, logger 500 and interpretation software |  | MPU/AN/WR/Vol.1/10/15 | 1 | 5000000 | 5000000 | 61001001/23050102/10000045 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Services | Capacity Development; Training, seminar and workshop |  | MPU/AN/WR/Vol.1/42/25 | 1 | 2000000 | 2000000 | 61001001/23050101/1000046 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Works | Water Supply project to Anambra West |  | MPU/AN/WR/Vol.1/03/17 | 1 | 10000000 | 10000000 | 61001001/23020105/10000050 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process
Services | Establishment of Water Sector Goverance Agencies and Institutional Framework |  | MPU/AN/WR/Vol.1/38/46 | 1 | 5000000 | 5000000 | 61001001/23020105/10000051 | ANSG | N | SELECTIVE | 2022-01-04 | 22/04/2022 | 25/04/2022 | 30/05/2022 | Timely completion of project and cost effectiveness of the procurement process